## Plan by Patwari
AGRISTACK BANDIPORA — PATWARI-WISE PLAN (planning start: 05-Sep-2026)
Rules: Each patwari finishes highest-% village first · Min 80/day per village · Complete within 25 days (deadline 30-Sep-2026) · Daily Target = MAX(80, ⌈Remaining ÷ 25⌉)
Colour key: | 1st — START NOW | 2nd — NEXT | 3rd | 4th+ | Completed
S.No | Patwari | Start Order | Tehsil | Village | Total Survey Nos | Submitted | % Completion | Daily Target | Expected Date of Completion
1 | Sajid Ahmad | Completed | AJAS | S.K.Payeen | 382 | 387 | 101.3% |  | Completed
2 | Mohd AMin | 1st — START NOW | AJAS | Ajas | 3312 | 2155 | 65.07% | 80 | 2026-09-20
3 | parviz Ahmad | 1st — START NOW | AJAS | Noorabad Ajas | 3159 | 1928 | 61.03% | 80 | 2026-09-21
4 | Altaf Ahmad Rather | 1st — START NOW | ALOOSA | Ashtangoo | 2204 | 2064 | 93.65% | 80 | 2026-09-07
5 | Sajad Ahmad Shah | 1st — START NOW | ALOOSA | Mangnipora | 2922 | 1885 | 64.51% | 80 | 2026-09-18
6 | Rayees Ahmad Kumar | 1st — START NOW | ALOOSA | Quil Muqam | 3558 | 2136 | 60.03% | 80 | 2026-09-23
7 | Mushtaq Ahmad Bhuroo | 1st — START NOW | ALOOSA | Malangam | 3547 | 1508 | 42.51% | 82 | 2026-09-30
8 | Bilal ahmad Dar | 1st — START NOW | ALOOSA | Aloosa | 6138 | 2564 | 41.77% | 143 | 2026-09-30
9 | Mudasir Yaseen | 1st — START NOW | ALOOSA | Kehnoosa | 4052 | 1656 | 40.87% | 96 | 2026-09-30
10 | Sajad Ahmad Bhat | 1st — START NOW | BANDIPORA | Garoora | 2966 | 2681 | 90.39% | 80 | 2026-09-09
11 | MUSHTAQ MUNTIZAR | 1st — START NOW | BANDIPORA | Nadihal | 1767 | 720 | 40.75% | 80 | 2026-09-19
12 |  | Completed | BANDIPORA | Brar | 902 | 934 | 103.5% |  | Completed
13 | Tufail Ahmad Bhat | 1st — START NOW | BANDIPORA | Onagam | 3446 | 2055 | 59.63% | 80 | 2026-09-23
14 | Aijaz Hassan Buhroo | 1st — START NOW | BANDIPORA | Nass | 832 | 741 | 89.06% | 140 | 2026-09-06
15 |  | 2nd — NEXT | BANDIPORA | Bandipora | 4783 | 1394 | 29.14% | 140 | 2026-09-30
16 |  | Completed | BANDIPORA | Dachigam | 698 | 724 | 103.7% |  | Completed
17 |  | Completed | BANDIPORA | Kharpora | 427 | 497 | 116.4% |  | Completed
18 |  | Completed | BANDIPORA | Papachan | 627 | 660 | 105.3% |  | Completed
19 | Mohammad rafiq | 1st — START NOW | BANDIPORA | Bonakoot | 5202 | 1311 | 25.2% | 156 | 2026-09-30
20 |  | Completed | BANDIPORA | Athwatoo | 1162 | 1180 | 101.5% |  | Completed
21 |  | Completed | BANDIPORA | Labkachal | 142 | 142 | 100% |  | Completed
22 |  | Completed | BANDIPORA | Weven | 1015 | 1026 | 101.1% |  | Completed
23 | AB RASHID KHAN | 1st — START NOW | BANDIPORA | Gund Dachina | 691 | 424 | 61.36% | 87 | 2026-09-09
24 |  | 2nd — NEXT | BANDIPORA | Chittibanday | 3473 | 1575 | 45.35% | 87 | 2026-09-30
25 | Mir Ehsanul Haq | 1st — START NOW | BANDIPORA | Gund Qasier | 643 | 637 | 99.07% | 151 | 2026-09-06
26 |  | 2nd — NEXT | BANDIPORA | Lowdara | 1189 | 644 | 54.16% | 151 | 2026-09-09
27 |  | 3rd | BANDIPORA | Gundipora Rampora | 1366 | 90 | 6.589% | 151 | 2026-09-18
28 |  | 4th | BANDIPORA | Konan Babagund | 1296 | 78 | 6.019% | 151 | 2026-09-26
29 |  | 5th | BANDIPORA | Madder | 728 | 1 | 0.1374% | 151 | 2026-09-30
30 |  | Completed | BANDIPORA | Checki Arsalakhan | 525 | 554 | 105.5% |  | Completed
31 |  | Completed | BANDIPORA | Gamaroo | 676 | 715 | 105.8% |  | Completed
32 |  | Completed | BANDIPORA | Takiya Ahmad Shah | 565 | 582 | 103% |  | Completed
33 | kaka ram | 1st — START NOW | BANDIPORA | Aragam | 1628 | 763 | 46.87% | 80 | 2026-09-16
34 | Wani Sajad Rasool | 1st — START NOW | BANDIPORA | Bhutto | 570 | 481 | 84.39% | 120 | 2026-09-06
35 |  | 2nd — NEXT | BANDIPORA | Ayatmulla | 1336 | 352 | 26.35% | 120 | 2026-09-14
36 |  | 3rd | BANDIPORA | Sonerwani | 1013 | 115 | 11.35% | 120 | 2026-09-22
37 |  | 4th | BANDIPORA | Ajar | 1066 | 59 | 5.535% | 120 | 2026-09-30
38 |  | Completed | BANDIPORA | Ahemshreif | 739 | 769 | 104.1% |  | Completed
39 |  | Completed | BANDIPORA | Check Reshipora | 303 | 319 | 105.3% |  | Completed
40 | Mehraj din | 1st — START NOW | BANDIPORA | Chuntimulla | 1450 | 1419 | 97.86% | 130 | 2026-09-06
41 |  | 2nd — NEXT | BANDIPORA | Kudara | 1189 | 508 | 42.72% | 130 | 2026-09-11
42 |  | 3rd | BANDIPORA | Sumlarshokbaba | 2780 | 262 | 9.424% | 130 | 2026-09-30
43 | Mudasir Sultan | 1st — START NOW | BANDIPORA | Arindardpora | 3909 | 1383 | 35.38% | 102 | 2026-09-30
44 |  | Completed | BANDIPORA | Shamthan | 201 | 208 | 103.5% |  | Completed
45 | MOHD SHAFI DAR | 1st — START NOW | BANDIPORA | Panjigam | 1879 | 1521 | 80.95% | 159 | 2026-09-08
46 |  | 2nd — NEXT | BANDIPORA | Kaloosa Nathpora | 4570 | 972 | 21.27% | 159 | 2026-09-30
47 | MOHD ARIF KUMAR | 1st — START NOW | BANDIPORA | Khayar | 973 | 805 | 82.73% | 173 | 2026-09-06
48 |  | 2nd — NEXT | BANDIPORA | Lawaypora | 1500 | 917 | 61.13% | 173 | 2026-09-10
49 |  | 3rd | BANDIPORA | Mantrigam | 4254 | 686 | 16.13% | 173 | 2026-09-30
50 |  | Completed | BANDIPORA | Chandaji | 257 | 257 | 100% |  | Completed
51 | Farooq ahmad | 1st — START NOW | BANDIPORA | Watapora | 2509 | 1513 | 60.3% | 186 | 2026-09-11
52 |  | 2nd — NEXT | BANDIPORA | Qazipora Putushai | 4884 | 1243 | 25.45% | 186 | 2026-09-30
53 | Irshad Ahmad Sheikh | 1st — START NOW | GUREZ | Shahpora Achoora (Churwan) | 2327 | 1914 | 82.25% | 80 | 2026-09-11
54 | Irfan Shafi Mir | 1st — START NOW | GUREZ | Kanzalwan Nail | 1072 | 882 | 82.28% | 80 | 2026-09-08
55 |  | 2nd — NEXT | GUREZ | Gulshanpora | 1275 | 781 | 61.25% | 80 | 2026-09-14
56 |  | Completed | GUREZ | Koragbal | 227 | 227 | 100% |  | Completed
57 | Aqib Ali Timroo | 1st — START NOW | GUREZ | Badwan | 1943 | 1122 | 57.75% | 80 | 2026-09-16
58 |  | Completed | GUREZ | Khandiyal | 714 | 718 | 100.6% |  | Completed
59 | Mohd Iqbal | 1st — START NOW | GUREZ | Markoot | 1528 | 1019 | 66.69% | 80 | 2026-09-12
60 |  | 2nd — NEXT | GUREZ | Dawar | 1172 | 524 | 44.71% | 80 | 2026-09-20
61 |  | Completed | GUREZ | Mastan Khopri | 550 | 565 | 102.7% |  | Completed
62 | Waseem Bashir | 1st — START NOW | HAJIN | Gund-I-Prang | 899 | 845 | 93.99% | 80 | 2026-09-06
63 |  | Completed | HAJIN | Madwan | 745 | 745 | 100% |  | Completed
64 |  | Completed | HAJIN | Sari Hari Karan Gund | 988 | 988 | 100% |  | Completed
65 | Mudasir Ahmad Parray | 1st — START NOW | HAJIN | Rakhi Hajin | 1191 | 978 | 82.12% | 80 | 2026-09-08
66 |  | 2nd — NEXT | HAJIN | Vijipara | 1652 | 963 | 58.29% | 80 | 2026-09-17
67 | Umar Jan | 1st — START NOW | HAJIN | Gundi Saderkote Sadunara | 2909 | 2004 | 68.89% | 101 | 2026-09-14
68 |  | 2nd — NEXT | HAJIN | Sadunara | 3363 | 1750 | 52.04% | 101 | 2026-09-30
69 | Nazeer Ahmad Lone | 1st — START NOW | HAJIN | Chandergeern | 1429 | 858 | 60.04% | 80 | 2026-09-13
70 |  | 2nd — NEXT | HAJIN | Kosumbagh | 2665 | 1263 | 47.39% | 80 | 2026-09-30
71 |  | Completed | HAJIN | Rakh-I-Malgam | 32 | 32 | 100% |  | Completed
72 |  | Completed | HAJIN | Zoonipora | 618 | 626 | 101.3% |  | Completed
73 | Ghulam Mohiddun | 1st — START NOW | HAJIN | Gundi Jahangir | 1485 | 789 | 53.13% | 80 | 2026-09-14
74 |  | 2nd — NEXT | HAJIN | Shah Gund | 2448 | 1205 | 49.22% | 80 | 2026-09-30
75 |  | Completed | HAJIN | Gund-I-Balkh | 258 | 265 | 102.7% |  | Completed
76 |  | Completed | HAJIN | Kanipora | 325 | 330 | 101.5% |  | Completed
77 | Mohd Ashraf Bhat | 1st — START NOW | HAJIN | Poshwari | 1514 | 1130 | 74.64% | 103 | 2026-09-09
78 |  | 2nd — NEXT | HAJIN | Baharabad | 2940 | 768 | 26.12% | 103 | 2026-09-30
79 |  | Completed | HAJIN | Gulshanpora | 829 | 846 | 102.1% |  | Completed
80 |  | Completed | HAJIN | Gundi Ramzan | 6 | 6 | 100% |  | Completed
81 | Adil Murtaza | 1st — START NOW | HAJIN | Gundi Boon | 830 | 715 | 86.14% | 112 | 2026-09-07
82 |  | 2nd — NEXT | HAJIN | Naidkhai | 4700 | 2027 | 43.13% | 112 | 2026-09-30
83 |  | Completed | HAJIN | Gulabwari | 19 | 19 | 100% |  | Completed
84 |  | Completed | HAJIN | Tangpora | 139 | 140 | 100.7% |  | Completed
85 | Aijaz Ahmad Wani | 1st — START NOW | HAJIN | Hajin | 7372 | 2492 | 33.8% | 196 | 2026-09-30
86 | mehraj abdullah | Completed | SUMBAL | Sumbal Inderkot | 980 | 1001 | 102.1% |  | Completed
87 |  | Completed | SUMBAL | Wahidpora | 899 | 923 | 102.7% |  | Completed
88 | Tawseef Ahmad | Completed | SUMBAL | Chewa | 1515 | 1531 | 101.1% |  | Completed
89 | Fariq Hussain | Completed | SUMBAL | Gaad Khud | 371 | 371 | 100% |  | Completed
90 |  | Completed | SUMBAL | Najin | 230 | 230 | 100% |  | Completed
91 | Summair Bashir Haji | Completed | SUMBAL | Zalpora | 402 | 402 | 100% |  | Completed
92 | Fayaz ahmad | 1st — START NOW | SUMBAL | Rakhi Shilvat | 2506 | 2234 | 89.15% | 80 | 2026-09-09
93 |  | Completed | SUMBAL | Shilvat | 658 | 687 | 104.4% |  | Completed
94 | aijaz Ahmad Bhat | 1st — START NOW | SUMBAL | Sarai Dangerpora | 2855 | 2584 | 90.51% | 80 | 2026-09-09
95 | irfan ahmad | 1st — START NOW | SUMBAL | Gndi Khalil | 1369 | 1173 | 85.68% | 80 | 2026-09-08
96 |  | 2nd — NEXT | SUMBAL | Trigam | 1948 | 1379 | 70.79% | 80 | 2026-09-15
97 | Feroz ahmad | 1st — START NOW | SUMBAL | Hilalabad | 2029 | 1490 | 73.44% | 80 | 2026-09-12
98 | ishfaq ahmad | 1st — START NOW | SUMBAL | Odina | 1145 | 926 | 80.87% | 80 | 2026-09-08
99 |  | 2nd — NEXT | SUMBAL | Ganastan | 2131 | 1289 | 60.49% | 80 | 2026-09-19
100 |  | Completed | SUMBAL | Malikpora | 204 | 206 | 101% |  | Completed
101 | waseem ahamd wagay | 1st — START NOW | SUMBAL | Asham | 3453 | 2338 | 67.71% | 80 | 2026-09-19
102 | Nisar Ahmad | 1st — START NOW | SUMBAL | Nowgam | 1109 | 877 | 79.08% | 80 | 2026-09-08
103 |  | 2nd — NEXT | SUMBAL | Rakh-I-Sultanpora | 2345 | 1096 | 46.74% | 80 | 2026-09-24
104 |  | Completed | SUMBAL | Gund-I-Nowgam | 531 | 532 | 100.2% |  | Completed
105 | muzaffar ahmad | 1st — START NOW | SUMBAL | Rkhi Asham | 6268 | 3087 | 49.25% | 128 | 2026-09-30
106 |  | Completed | SUMBAL | Shadipora | 676 | 678 | 100.3% |  | Completed
107 | Manzoor ahmad | 1st — START NOW | TULAIL | Jurnial | 769 | 698 | 90.77% | 80 | 2026-09-06
108 |  | 2nd — NEXT | TULAIL | Dengithal | 302 | 267 | 88.41% | 80 | 2026-09-07
109 |  | 3rd | TULAIL | Barnaie | 429 | 341 | 79.49% | 80 | 2026-09-08
110 |  | Completed | TULAIL | Kilshay Payeen | 325 | 325 | 100% |  | Completed
111 |  | Completed | TULAIL | Manzgund | 281 | 281 | 100% |  | Completed
112 |  | Completed | TULAIL | Purana Tulail | 166 | 166 | 100% |  | Completed
113 |  | Completed | TULAIL | Zedgey | 192 | 192 | 100% |  | Completed
114 | adil ali | 1st — START NOW | TULAIL | Baduaab | 737 | 661 | 89.69% | 80 | 2026-09-06
115 |  | 2nd — NEXT | TULAIL | Gujran | 798 | 433 | 54.26% | 80 | 2026-09-11
116 |  | Completed | TULAIL | Abdullian | 286 | 286 | 100% |  | Completed
117 |  | Completed | TULAIL | Malangam | 421 | 421 | 100% |  | Completed
118 | umar afzal | 1st — START NOW | TULAIL | Saradaab | 633 | 496 | 78.36% | 80 | 2026-09-07
119 |  | 2nd — NEXT | TULAIL | Buglinder | 646 | 484 | 74.92% | 80 | 2026-09-09
120 |  | 3rd | TULAIL | Neeru | 517 | 362 | 70.02% | 80 | 2026-09-11
121 |  | 4th | TULAIL | Budugam | 822 | 164 | 19.95% | 80 | 2026-09-19
122 |  | Completed | TULAIL | Gund Gul Sheikh | 222 | 224 | 100.9% |  | Completed
123 |  | Completed | TULAIL | Hussangam | 362 | 362 | 100% |  | Completed
124 |  | Completed | TULAIL | Wazirthal | 128 | 128 | 100% |  | Completed
|  |  |  | TOTAL | 193229 | 111061 | 57.48% | 4525 | 2026-09-30
Note: Daily Target on each row = the patwari's daily submission rate while working on that village. Since a patwari works one village at a time, the district-wide daily total in the TOTAL row is the sum of ONE rate per patwari.

## 5-Day Completion (Tehsil)
5-DAY COMPLETION TIMELINE — TEHSIL WISE (planning start 05-Sep-2026)
How many villages complete in each 5-day window · Numbers = village counts
Tehsil | Total Villages | Already Completed | 06–10 Sep | 11–15 Sep | 16–20 Sep | 21–25 Sep | 26–30 Sep | To Complete
AJAS | 3 | 1 | 0 | 0 | 1 | 1 | 0 | 2
ALOOSA | 6 | 0 | 1 | 0 | 1 | 1 | 3 | 6
BANDIPORA | 43 | 14 | 10 | 3 | 3 | 2 | 11 | 29
GUREZ | 9 | 3 | 1 | 3 | 2 | 0 | 0 | 6
HAJIN | 24 | 10 | 4 | 3 | 1 | 0 | 6 | 14
SUMBAL | 21 | 10 | 5 | 2 | 2 | 1 | 1 | 11
TULAIL | 18 | 9 | 6 | 2 | 1 | 0 | 0 | 9
TOTAL | 124 | 47 | 27 | 13 | 11 | 5 | 21 | 77
Buckets are calendar-day windows from 06-Sep-2026 (day 1). A village is placed in the bucket its Expected Date of Completion falls in. "Already Completed" = villages with 100%+ submission on 03-Sep data.